| Document | Status | Updated |
| --- | --- | --- |
| 90-Day Sprint Plan | Draft | January 2026 |

# Pearl Marketing 90-Day Sprint Plan

## January 15 - April 15, 2026

## What This Plan Achieves

Establish Pearl as a visible authority in real estate ahead of Series B.

## Supporting Documents

| Document | Purpose |
| --- | --- |
| 2026 Annual Marketing Plan | Full year strategy and budget |
| Organic Content Calendar | Q1-Q4 organic content, pillar reference |
| PR Tracker | Atkinson deliverables, media coverage, podcasts |
| Surge Tracker | Paid campaigns, geo-fence, budget tracking |
| Partnership Audit | Costs, benefits, marketing rights |
| Conference Audit | Speaking/booth costs, event priorities |
| PR Messaging Guide | Headlines, talking points for Atkinson PR |

### Campaign Types

| Type | Q1 Campaigns | Cadence |
| --- | --- | --- |
| Always-On | LinkedIn ads, Social media, SEO/Content (Front Page Sage), PR outreach (Atkinson) | Continuous |
| Surge | Campaign Sprint (report launch), Geo-fence (Natl Home Perf Conf) | Around key moments |

### Q1 Objectives

| Objective | Target |
| --- | --- |
| Pillar content pieces with media coverage | 3 |
| Major industry speaking events | 2+ |
| Podcast appearances secured | 12-18 |
| Derivatives per pillar (emails, infographics, ads) | 8-10 |
| Geo-fence campaigns (of 10 annual) | 1 |

## Pillar Content (Flagship Pieces)

Each pillar generates 20+ derivative pieces: email sequences, infographics, ad creatives, video clips. Blog posts and social media are tracked separately below.

| Pillar | Launch | Owner | Audience |
| --- | --- | --- | --- |
| State of Home Performance 2026 | April | Marketing | B2B + B2C |
| 2026 Home Performance Consumer Survey | Mar | Marketing | B2C |
| What Buyers Want (Listings Don't Show) | Weeks 9-10 (Mar) | Marketing | B2C |

## Target Audiences

| Audience | Segment | Description |
| --- | --- | --- |
| Primary | B2B | Real estate agents, brokers |
| Primary | B2C | Home buyers |

## Q1 Budget (~$102,320)

| Category | Audience | Details | Budget |
| --- | --- | --- | --- |
| LinkedIn Always-On | B2B | 12 wks × $3K | $36,000 |
| Campaign Sprint | B2B | 2 wks × $7.5K | $15,000 |
| Geo-fence: Inman Connect NYC | B2B | CANCELLED | — |
| Geo-fence: Natl Home Perf Conf | B2B | Apr 13 (2.8K attend) | $16,320 |
| Atkinson (PR) | B2B | 3 months | $13,500 |
| Front Page Sage (SEO) | B2C | 3 months | $9,000 |
| Content Production | B2B+B2C | Report, video | $12,500 |

### Atkinson PR Services

Compare base retainer vs. expanded proposal:

| Deliverable | Base ($4,500/mo) | Expanded (+TBD) |
| --- | --- | --- |
| Media pitches | 20/month | 20/month |
| Story concepts + pitch memos | 5/month | 5/month |
| Media monitoring report | Monthly | Monthly |
| Status meeting | Monthly | Monthly |
| Press releases | Drafting only* | 2-3/mo on wire |
| Podcast pitches | — | 12/month |
| Op-eds/commentaries | — | 1/month |
| Local TV/radio pitches | — | Ongoing |
| Exec strategy calls | — | Monthly |

*Wire distribution costs billed separately

Decision needed: proceed with expanded scope or stay with base retainer?

## Q1 Events (by date)

1 of 10 annual geo-fence campaigns occurs in Q1

| Event | Date | Attendance | Marketing Support |
| --- | --- | --- | --- |
| Inman Connect NYC | Feb 3 | 2,000-4,000 | Insider dinner support (BD) |
| ICE Experience | Mar 16 | 3,000+ | Social only |
| Natl Home Perf Conf | Apr 13 | 2,800 | Geo-fence + speaking |

## 90-Day Goals

| Goal | Metric | Target | Audience |
| --- | --- | --- | --- |
| Media | Tier-1 placements | 2+ | B2B+B2C |
| Media | Total mentions | 15+ | B2B+B2C |
| Podcasts | Booked | 12-18 | B2B+B2C |
| Speaking | Events | 2+ | B2B |
| Content | Pillar pieces | 3 | B2B+B2C |
| Content | B2B blog posts | 3 (ramp with AI) | B2B |
| Content | B2C blog posts (Front Page Sage) | 12 | B2C |
| Content | Derivatives (emails, infographics, ads) | 20+ | B2B+B2C |
| Paid | Geo-fence campaigns | 1 | B2B |
| Foundation | Report downloads | 500+ | B2C |

## Social Media Strategy

### B2B Channels (Real Estate Agents)

| Platform | Baseline | During Surges | Owner |
| --- | --- | --- | --- |
| LinkedIn | 3x/week | Daily | Marketing |
| X (Twitter) | 3-5x/week | 5-7x/week | Marketing |

### B2C Channels (Homeowners)

| Platform | Baseline | During Surges | Owner |
| --- | --- | --- | --- |
| Meta (Facebook) | 2-3x/week | 4-5x/week | Marketing |
| Blue Sky | 2-3x/week | 4-5x/week | Marketing |

### Recruitment Only (Pearl Culture)

| Platform | Frequency | Content Focus | Owner |
| --- | --- | --- | --- |
| Instagram | 2-3x/week | Team, culture, careers | Marketing/HR |

Note: Instagram is NOT used for B2B or B2C marketing—recruitment and employer branding only.

## Week-by-Week Execution

Color key: Light blue = B2B | Light green = B2C | White = Both/Culture

### WEEKS 1-2: Foundation (Jan 15-28)

| Audience | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Both | Complete partnership audit | Marketing + Owners | Confirmed Q1 partnership usage |
| Both | Complete conference audit | Marketing + BD | Confirmed Q1 event priorities |
| B2B | Finalize report | Marketing + AI | Draft complete |
| B2B | Brief Atkinson on Q1 priorities | Marketing | Kick-off call |
| B2B | Speaker kit | Marketing + AI | Messaging doc |
| Both | Logo audit | Marketing | Guidelines confirmed |
| B2B | Confirm Inman Connect NYC attendance | Marketing + BD | Status confirmed |
| Both | Media pitches (10) | Atkinson | Targeted outreach |
| Both | Story concepts (2-3) | Atkinson | Pitch memos |
| B2C | Blog posts (2) | Front Page Sage | SEO/AI-optimized |
| B2B | LinkedIn posts | Marketing | 6 posts |
| B2B | X posts | Marketing | 6-10 posts |
| B2C | Meta posts | Marketing | 4-6 posts |
| B2C | Blue Sky posts | Marketing | 4-6 posts |
| Culture | Instagram posts | Marketing/HR | 4-6 posts |

Milestone: Foundation ready, Inman Connect NYC prep complete

### WEEKS 3-4: Inman Connect NYC (Jan 29 - Feb 11)

SURGE PERIOD: Daily posting on B2B channels during Inman Connect NYC

| Audience | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Both | Launch report | Marketing | Report live, gated |
| B2B | Insider dinner support | Marketing | Collateral, social for BD event |
| Both | Email blast | Marketing | Announcement |
| Both | Event content | Founders | Photos, quotes |
| Both | Media pitches (10) | Atkinson | Report launch push |
| Both | Story concepts (2-3) | Atkinson | Pitch memos |
| Both | Podcast pitches (6) | Atkinson | Initial outreach |
| B2C | Blog posts (2) | Front Page Sage | SEO/AI-optimized |
| B2B | Blog post (1) | Marketing + AI | Report companion piece |
| B2B | LinkedIn posts - SURGE | Marketing | Daily (14+ posts) |
| B2B | X posts - SURGE | Marketing | Daily (14+ posts) |
| B2C | Meta posts | Marketing | 4-6 posts |
| B2C | Blue Sky posts | Marketing | 4-6 posts |
| Culture | Instagram posts | Marketing/HR | 4-6 posts |

Milestone: Inman Connect NYC executed, report launched, media hits

### WEEKS 5-6: Momentum (Feb 12-25)

| Audience | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Both | Report derivatives: emails, infographics, ads | Marketing + AI | 8-10 pieces |
| B2B | Retargeting | Marketing | Always-on |
| B2B | Inman Connect NYC follow-up | Marketing | Lead nurture |
| Both | Media pitches (10) | Atkinson | Continued outreach |
| Both | Story concepts (2-3) | Atkinson | Pitch memos |
| Both | Podcast pitches (6) | Atkinson | Ongoing outreach |
| Both | Media monitoring report | Atkinson | Monthly summary |
| B2C | Blog posts (2) | Front Page Sage | SEO/AI-optimized |
| B2B | Blog post (1) | Marketing + AI | User-friendly agent content |
| Both | Monthly performance report | Front Page Sage | Analytics review |
| B2B | LinkedIn posts | Marketing | 6 posts |
| B2B | X posts | Marketing | 6-10 posts |
| B2C | Meta posts | Marketing | 4-6 posts |
| B2C | Blue Sky posts | Marketing | 4-6 posts |
| Culture | Instagram posts | Marketing/HR | 4-6 posts |

Milestone: Podcast pipeline started, content flowing

### WEEKS 7-8: Content Engine (Feb 26 - Mar 11)

| Audience | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| B2C | Second pillar draft | Marketing + AI | Complete |
| Both | Q2 calendar | Marketing + AI | Drafted |
| B2B | Case study | Marketing + AI | 1 complete |
| B2B | ICE Experience prep | Marketing | Collateral ready |
| Both | Media pitches (10) | Atkinson | Continued outreach |
| Both | Story concepts (2-3) | Atkinson | Pitch memos |
| Both | Podcast pitches (6) | Atkinson | Ongoing outreach |
| Both | Podcast bookings update | Atkinson | 4-6 confirmed |
| B2C | Blog posts (2) | Front Page Sage | SEO/AI-optimized |
| B2B | LinkedIn posts | Marketing | 6 posts |
| B2B | X posts | Marketing | 6-10 posts |
| B2C | Meta posts | Marketing | 4-6 posts |
| B2C | Blue Sky posts | Marketing | 4-6 posts |
| Culture | Instagram posts | Marketing/HR | 4-6 posts |

Milestone: Content engine running, events prepped

### WEEKS 9-10: Spring Prep (Mar 12-25)

ICE Experience (Mar 16): Social coverage on B2B channels

| Audience | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| B2C | Launch pillar 2 | Marketing | Blog, social, email |
| B2B | ICE Experience | BD + Marketing | Social coverage |
| B2B | Confirm RESO Spring | Product + Marketing | Status confirmed |
| B2B | Confirm The Gathering | BD + Marketing | Status confirmed |
| Both | Podcasts ongoing | Founders | 6+ completed |
| Both | Q1 metrics | Marketing | Dashboard |
| Both | Media pitches (10) | Atkinson | Continued outreach |
| Both | Story concepts (2-3) | Atkinson | Pitch memos |
| Both | Podcast pitches (6) | Atkinson | Ongoing outreach |
| Both | Media monitoring report | Atkinson | Monthly summary |
| B2C | Blog posts (2) | Front Page Sage | SEO/AI-optimized |
| Both | Monthly performance report | Front Page Sage | Analytics review |
| B2B | LinkedIn posts | Marketing | 6 posts + ICE coverage |
| B2B | X posts | Marketing | 6-10 posts + ICE coverage |
| B2C | Meta posts | Marketing | 4-6 posts |
| B2C | Blue Sky posts | Marketing | 4-6 posts |
| Culture | Instagram posts | Marketing/HR | 4-6 posts |

Milestone: Q2 events confirmed, Q1 documented

### WEEKS 11-12: Assessment (Mar 26 - Apr 15)

SURGE PERIOD: Daily posting on B2B channels during Natl Home Perf Conf (Apr 13)

| Audience | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Both | 90-day assessment | Marketing | Leadership report |
| B2B | Natl Home Perf Conf | BD + Marketing | Speaking + geo-fence |
| Both | Q2 calendar final | Marketing | Confirmed |
| Both | Budget reconcile | Marketing | Spend vs plan |
| Both | Q2 content plan | Marketing + AI | Full quarter |
| B2B | Investor summary | Marketing | Key stats |
| Both | Media pitches (10) | Atkinson | Continued outreach |
| Both | Story concepts (2-3) | Atkinson | Pitch memos |
| Both | Podcast pitches (6) | Atkinson | Ongoing outreach |
| Both | Q1 media summary | Atkinson | Coverage report |
| B2C | Blog posts (2) | Front Page Sage | SEO/AI-optimized |
| B2B | Blog post (1) | Marketing + AI | Home performance tie-in |
| Both | Q1 performance report | Front Page Sage | Full quarter review |
| B2B | LinkedIn posts - SURGE | Marketing | Daily during conf (14+ posts) |
| B2B | X posts - SURGE | Marketing | Daily during conf (14+ posts) |
| B2C | Meta posts | Marketing | 4-6 posts |
| B2C | Blue Sky posts | Marketing | 4-6 posts |
| Culture | Instagram posts | Marketing/HR | 4-6 posts |

Milestone: Sprint complete, Q2 ready

## Q2 Event Prep (During Sprint)

Events occurring shortly after sprint ends require prep during Q1:

### Immediate Post-Sprint Events

| Event | Date | Days After Sprint | Marketing Support |
| --- | --- | --- | --- |
| RESO Spring | Apr 21 | 6 days | Social/collateral |
| The Gathering | Apr 27 | 12 days | Social/collateral |
| BPA Clean Energy Homes | May 28-29 | 6 weeks | Speaking opp? |
| NAR Trade Expo | Jun 15 | 9 weeks | Geo-fence |
| NEEP Summit | Jun 23-26 | 10 weeks | Policy/P3 |

### Q2 Prep Tasks (Complete by Apr 15)

| Task | For Event | Owner | Due |
| --- | --- | --- | --- |
| Confirm attendance | RESO Spring | Product + Marketing | Mar 15 |
| Confirm attendance | The Gathering | BD + Marketing | Mar 15 |
| Submit speaking proposal | BPA Clean Energy Homes | Marketing | Mar 1 |
| Geo-fence campaign setup | NAR Trade Expo | Marketing | Apr 15 |
| Collateral refresh | All Q2 events | Marketing | Apr 1 |
| Q2 content calendar | All | Marketing + AI | Apr 15 |
| Travel/logistics | All Q2 events | BD + Marketing | Apr 1 |

### Additional Q2 Conferences to Monitor

From company conference tracker - evaluate for Q2 participation:

| Event | Date | Location | Audience | Decision By |
| --- | --- | --- | --- | --- |
| ACCA National | Mar 15-18 | Las Vegas | Contractors | Feb 1 |
| RESNET | Mar 17-19 | San Antonio | HERS/New Build | Feb 1 |
| Inman Connect SD | Jul 28 | San Diego | Real Estate | May 1 |
| ACEEE Summer Study | Aug 2-7 | Pacific Grove | Policy/P3 | May 1 |

## Success Criteria (Day 90)

### B2B Goals (Real Estate Agents/Brokers)

| Goal | Target |
| --- | --- |
| Tier-1 media mentions | 2+ |
| Total media mentions | 10+ |
| Podcast appearances booked | 12+ |
| Geo-fence campaigns | 1 (of 10 annual) |
| B2B blog posts | 3 (ramp with AI) |
| LinkedIn/X cadence | Maintained |
| Speaker kit | Distributed |

### B2C Goals (Homeowners/Buyers)

| Goal | Target |
| --- | --- |
| Report downloads | 500+ |
| B2C blog posts (Front Page Sage) | 12 |
| Meta/Blue Sky cadence | Maintained |
| pearlscore.com consumer page views | Baseline established |
| Consumer email list growth | Tracked |

### Both Audiences

| Goal | Target |
| --- | --- |
| Q2 calendar | Confirmed |
| Derivatives from pillars (emails, infographics, ads) | 20+ |

### Stretch Goals

| Audience | Goal |
| --- | --- |
| B2B | Speaking slot secured |
| B2B | Partnership activated |
| B2B | Case study published |
| B2C | Consumer survey launched |
| Both | 25% website traffic increase |