| Document | Status | Updated |
| --- | --- | --- |
| 2026 Annual Plan | Draft | January 2026 |

# Pearl 2026 Marketing Plan

## Strategic Objectives

- Establish Pearl as THE authority on home performance ratings

- Build investor credibility ahead of Series B

- Create visible market momentum within first 90 days

- Articulate Pearl's moat — 92M homes scored, proprietary methodology, first-mover data advantage, key partnerships (verify usage rights)

## Supporting Documents

| Document | Purpose |
| --- | --- |
| Organic Content Calendar | Q1-Q4 organic content, pillar reference |
| PR Tracker | Atkinson deliverables, media coverage, podcasts |
| Surge Tracker | Paid campaigns, geo-fence, budget tracking |
| Sprint Plans: Q1 ¦ Q2 ¦ Q3 ¦ Q4 | Quarterly execution plans |
| Partnership Audit | Costs, benefits, marketing rights |
| Conference Audit | Speaking/booth costs, event priorities |

### Q1 Foundation Tasks

Complete by end of Weeks 1-2 to confirm Q1 priorities:

- Complete Partnership Audit — confirm costs, benefits, and marketing usage rights for each partnership

- Complete Conference Audit — confirm which events to attend/sponsor in Q1 and beyond

## Target Audiences

Color key: Light blue = B2B | Light green = B2C

| Segment | Priority | Description |
| --- | --- | --- |
| B2B | Primary | Real estate agents, brokers |
| B2C | Primary | Home buyers |

## The Approach: Drumbeat + Surge

Maintain consistent baseline presence while amplifying around key moments.

| Type | Campaigns | Cadence |
| --- | --- | --- |
| Always-On | LinkedIn ads, Social media, SEO/Content, PR outreach | Year-round |
| Surge | Campaign Sprints (pillar launches), Geo-fence (events), Regional B2C | Around key moments |

## 2026 Budget Overview

Color key: Light blue = B2B | Light green = B2C | White = Both

### Media Buy: $623,200

| Audience | Campaign | Details | Budget |
| --- | --- | --- | --- |
| B2B | LinkedIn Always-On | 48 wks × $3K | $144,000 |
| B2B | Campaign Sprints | 8 × 2 wks × $7.5K | $120,000 |
| B2B | Geo-fenced Events | 10 × $16,320 | $163,200 |
| B2C | Regional Awareness | 20 wks × $3K | $60,000 |
| B2C | Regional ILS Launch | 16 wks × $8.5K | $136,000 |
| Both | Total |  | $623,200 |

### Campaign Sprint Details (8 campaigns):

- 4 Whitepapers

- 2 Research Reports

- 2 Product Milestones

### Services: $150,000

In-house + AI, fixed vendors, plus contractors.

## Vendor Deliverables

Color key: Light blue = B2B | Light green = B2C | White = Both

### Atkinson PR Services

Compare base retainer vs. expanded proposal:

| Deliverable | Base ($4,500/mo) | Expanded ($11,000/mo) |
| --- | --- | --- |
| Media pitches | 20/month | 60-80/month |
| Story concepts + pitch memos | 5/month | 5-7/month |
| Media monitoring report | Monthly | Monthly |
| Status meeting | Monthly | Monthly |
| Press releases | As requested* | 2-3/month |
| Op-eds/commentaries | — | 1-2/month |
| Local TV/radio pitches | — | Ongoing |
| Exec strategy calls to explore SCORE data for news-worthy insights. | — | Monthly |

*Wire distribution costs billed separately

Goal: Establish Pearl as THE authority on home performance and elevate Cynthia/Robin as industry experts.

#### Expansion Partners

Atkinson has established partnerships to scale capacity if needed:

| Partner | Specialty | Notes |
| --- | --- | --- |
| Weber Shandwick Collective | Full-service PR | 2nd largest PR firm globally; Atkinson worked there 10 years |
| 1631 Digital | Geo-fencing | Digital advertising and location-based targeting |
| Kenzee Communications | Social media | Minority-owned; focus on multi-family space |

### Front Page Sage (~$4,000/month)

| Audience | Deliverable | Frequency | Notes |
| --- | --- | --- | --- |
| B2C | SEO/GEO blog posts | 4/month | 1 credit each; LLM + search optimized |
| B2C | LinkedIn posting | Weekly | Included, no credits |
| — | Consulting calls | Weekly | Included, no credits |
| — | Monthly report | Monthly | Performance analysis |
| B2C | Hub/pillar pages | As needed | 2 credits each |
| B2C | Case studies | As needed | 2 credits each |

7 credits/month total. Focus: SEO + GEO (Generative Engine Optimization) to position Pearl as an authoritative source in LLMs and search.

Note: FPS content targets consumers (homeowners/buyers) searching for home performance info. B2B agent/broker content is produced by Marketing + AI.

⚠️ FLAG: FPS contract includes LinkedIn posting, but LinkedIn is our B2B channel. Need to discuss: Should FPS post B2C content to LinkedIn, or reallocate those credits?

### Marketing + AI Content Production

| Audience | Deliverable | Frequency | Notes |
| --- | --- | --- | --- |
| B2B | Blog posts | 1/month (ramp with AI) | Agent/broker focused, user-friendly |
| Varies | Pillar content pieces | 1/month | See Content Strategy for audience by pillar |
| Varies | Content derivatives | 20+/pillar | Social, email, ads from each pillar |
| Both | Email sequences | As needed | Nurture campaigns |
| Both | Ad copy | Per campaign | Geo-fence, LinkedIn, Meta |

## BD Event Calendar 2026

Budget: 10 geo-fence campaigns at $16,320 each ($163,200 total)

### BD/Real Estate Events by Date

| Event | Date | Attendance | Geo-fence? |
| --- | --- | --- | --- |
| Inman Connect NYC | Feb 3 | 2,000-4,000 | No (cancelled) |
| ICE Experience | Mar 16 | 3,000+ | No (mortgage focus) |
| Natl Home Perf Conf | Apr 13 | 2,800 | Yes |
| RESO Spring | Apr 21 | 400 | No (too small) |
| The Gathering | Apr 27 | ~710 | No (too small) |
| NAR Trade Expo | Jun 15 | 8,000+ | Yes |
| Inman Connect SD | Jul 28 | 2,000-4,000 | Yes |
| Blueprint | Sep 22 | 3,000+ | Yes |
| CMLS Open House | Sep 29 | ~1,000 | Yes |
| Compass Retreat | Oct 1 | 2,200+ | Yes |
| REimagine! | Oct 6 | 3,000+ | Yes |
| Zillow Unlock | Oct 13 | 2,500 | Yes |
| NAR NXT | Nov 6 | 12,000+ | Yes |

9 geo-fence events confirmed; Inman Connect NYC cancelled (budget to be reallocated).

4 events (Inman Connect NYC, ICE Experience, RESO Spring, The Gathering) receive social/collateral support only.

### Additional Conferences to Consider

Events from company conference tracker not on BD priority list:

| Event | Date | Location | Est. Attendance | Audience |
| --- | --- | --- | --- | --- |
| Home SPARK 2026 | Jan 6-9 | Amelia Island | 500+ | Contractors |
| Midwest Energy Solutions | Jan 28-31 | Chicago | 800+ | Policy/P3 |
| AHR Expo | Feb 2-4 | Las Vegas | 40,000+ | HVAC/Contractors |
| NASEO Policy Outlook | Feb 3-6 | Washington DC | 300+ | Policy/P3 |
| EGIA EPIC 2026 | Feb 12-13 | Las Vegas | 1,500+ | Contractors |
| Momentum Building Conf | Feb 19-20 | Des Moines | 300+ | Policy/P3 |
| ACCA National | Mar 15-18 | Las Vegas | 2,000+ | HVAC/Contractors |
| RESNET | Mar 17-19 | San Antonio | 1,000+ | HERS/New Build |
| BPA Clean Energy Homes | May 28-29 | Saratoga Springs | 500+ | Policy/P3 |
| NEEP Summit 2026 | Jun 23-26 | Baltimore | 400+ | Policy/P3 |
| ACEEE Summer Study | Aug 2-7 | Pacific Grove | 500+ | Policy/P3 |
| Service World Expo | Nov 9-12 | Las Vegas | 2,000+ | Contractors |
| RE+ 2026 | Nov 16-19 | Las Vegas | 25,000+ | Solar/Renewables |

Note: RE+ (25K+) offers significant reach if solar/renewables audience is priority.

## 2026 Moment Calendar

Color key: Light blue = B2B | Light green = B2C | White = Both

Includes 8 campaign sprints (pillar launches) and 9 geo-fenced events.

| Audience | Quarter | Moment | Type |
| --- | --- | --- | --- |
| Both | Q1 | State of Home Performance Report | Campaign Sprint (Whitepaper) |
| Both | Q1 | Inman Connect NYC | Conference + Dinner |
| B2B | Q1 | Natl Home Perf Conf | Conference + Geo |
| B2C | Q2 | 2026 Consumer Survey | Campaign Sprint (Research) |
| B2C | Q2 | What Buyers Want | Campaign Sprint (Whitepaper) |
| B2B | Q2 | NAR Trade Expo | Conference + Geo |
| B2B | Q2 | RESO Spring | Conference |
| B2B | Q3 | Inman Connect San Diego | Conference + Geo |
| B2C | Q3 | Home Resilience | Campaign Sprint (Whitepaper) |
| B2C | Q3 | Regional B2C push | Paid Media |
| B2B | Q3 | Blueprint | Conference + Geo |
| B2B | Q3 | CMLS Open House | Conference + Geo |
| B2C | Q4 | True Cost of Homeownership | Campaign Sprint (Research) |
| B2B | Q4 | Compass Retreat | Conference + Geo |
| B2B | Q4 | REimagine! | Conference + Geo |
| B2B | Q4 | Zillow Unlock | Conference + Geo |
| B2B | Q4 | NAR NXT | Conference + Geo |
| Both | Q4 | Year in Review | Campaign Sprint (Report) |

## Channel Strategy

Color key: Light blue = B2B | Light green = B2C | White = Both

| Audience | Channel | Owner | Approach |
| --- | --- | --- | --- |
| Both | PR/Media | Atkinson | 20 pitches/mo |
| B2C | SEO/GEO Content | Front Page Sage | 4 posts/mo (LLM + search optimized) |
| B2B | Blog | Marketing + AI | 1 post/mo (ramp with AI) |
| Both | Paid Media | Marketing | Surge + geo |
| Both | Social Media | Marketing + AI | By platform (see below) |
| B2B | Speaking | Cross-functional | Marketing supports |

## Social Media Strategy

### B2B Channels (Real Estate Agents)

| Platform | Owner | Frequency | Content Focus |
| --- | --- | --- | --- |
| LinkedIn | Marketing | Daily (surges), 3x/wk (baseline) | Industry news, thought leadership |
| X (Twitter) | Marketing | 3-5x/week | Real estate conversations, news |

### B2C Channels (Homeowners)

| Platform | Owner | Frequency | Content Focus |
| --- | --- | --- | --- |
| Meta (Facebook) | Marketing | 2-3x/week | Home tips, Pearl SCORE education |
| Blue Sky | Marketing | 2-3x/week | Community engagement, early adopters |

### Recruitment Only (Pearl Culture)

| Platform | Owner | Frequency | Content Focus |
| --- | --- | --- | --- |
| Instagram | Marketing/HR | 2-3x/week | Team highlights, culture, careers |

Note: Instagram is NOT used for B2B or B2C marketing—recruitment and employer branding only.

## Content Strategy

Monthly pillar model: One flagship piece → 20+ derivatives

Color key: Light blue = B2B | Light green = B2C | White = Both

| Audience | Month | Pillar | Owner |
| --- | --- | --- | --- |
| Both | Jan/Feb | State of Home Performance | Marketing |
| B2C | Mar | 2026 Home Performance Consumer Survey | Marketing |
| B2C | Mar | What Buyers Want | Marketing |
| B2B | May | Agent Guide to Pearl | Marketing |
| B2C | Jul | Home Resilience | Marketing |
| B2C | Sep | True Cost of Homeownership | Marketing |
| Both | Nov | Year in Review | Marketing |

## Success Metrics

| Audience | Metric | Target |
| --- | --- | --- |
| Both | Tier-1 media | 6+ annually |
| Both | Podcasts | 4-6 |
| B2B | Speaking | 6-8 annually |
| B2C | Traffic growth | 25% QoQ |
| B2C | Home claims | Increasing |

## Strategic Decision: PR Strategy for Series B

Goal: Establish Pearl as the go-to leader in home performance rating, build investor credibility, and ward off competition.

| Factor | Atkinson (Expanded) | Larger PR Firm |
| --- | --- | --- |
| Cost | TBD (currently $4,500/mo) | TBD |
| Pearl knowledge | Deep - 2+ years working together | Ramp-up required |
| Tier-1 targeting | Specific journalists identified; some existing Pearl relationships | Unknown |
| Startup/VC expertise | Can scale via Weber Shandwick partnership | Potentially core specialty |
| Speed to market | Immediate - Q1 pitching calendar ready | Onboarding time needed |
| Scalability | Weber Shandwick available if capacity needed | Built-in team depth |

Key Question: Does a larger firm get us into Tier-1 faster, or does Atkinson's existing Pearl knowledge and ready-to-execute plan provide a head start?

Note: Atkinson's proposal includes a pitching calendar targeting NYT, WSJ, WaPo, NPR, Consumer Reports, Axios, and others. Some journalists have existing Pearl relationships (e.g., WSJ reporter who previously covered Pearl). Weber Shandwick (2nd largest PR firm globally) is available as expansion partner if capacity is needed.

## Other Discussion Questions

- Which moments to prioritize if budget constrained?

- Realistic speaking engagement budget?

- Who owns conference decisions (Marketing vs BD)?

- Which partnerships to actively support?

- How to balance B2B vs B2C messaging?