OPERATIONAL BRIEF

2026 Marketing Strategy Overview

| DEPARTMENT: | Marketing | PROJECT: | 2026 Marketing Strategy | FROM: | Kat |
| --- | --- | --- | --- | --- | --- |
| DATE: | 2026-01-15 | PROJECT #: | MKT-000052 | DRAFT: | 1.0 |

# I. 2026 Marketing Strategy

TABLE OF CONTENTS

A. Background

B. Project Overview

C. How It Is Today

D. Objectives

E. Success Criteria

F. Strategic Framework

G. Budget Framework

H. 2026 Moment Calendar

I. Channel Strategy

J. Resource Model

K. Discussion Questions

A. Background

How did we get here in a nutshell?

1. Pearl has built the first national home performance rating system, scoring all 92 million US single-family homes across five pillars: Safety, Comfort, Operations, Resilience, and Energy. The infrastructure is built. The technology works. Now Pearl must establish itself as THE authority on home performance standards.

2. This marketing strategy supports Series B fundraising by creating visible market momentum and positioning Pearl as the inevitable category leader in home performance data.

3. The strategy adopts a 'Moments, Not Months' approach—concentrating resources around 4-6 major moments per year rather than spreading budget thin across steady-state activities.

B. Project Overview

Briefly describe the purpose of the exercise.

1. Instigator: Marketing Leadership / Board

2. Need and Motivation: The board requires visible market momentum ahead of Series B. Investors need to see press coverage, industry adoption signals, and Pearl SCORE becoming a recognized term. This strategy creates that evidence within 90 days and sustains it through 2026.

3. What We Want Done: Execute a concentrated marketing strategy that establishes Pearl as the definitive authority on home performance ratings through strategic conference presence, flagship content, systematic podcast appearances, and moment-based paid media surges.

C. How It Is Today

Define the situation as it is today—specifically, the problem you are trying to solve.

1. Pearl has strong credentials (DOE partnership, NAR/RESO relationships, Inman Award, 200K+ certified homes) but limited visibility in the real estate agent community—our primary target audience.

2. The marketing team is lean (one person + AI assistance + outsourced vendors), requiring ruthless prioritization and efficient execution.

3. Existing vendor relationships:

a) Atkinson Strategic Group (PR): $4,500/month—media pitches, press releases, podcast pitching

b) Front Page Sage (SEO): ~$3,000-5,000/month—B2C content, LinkedIn posting

4. Partnership benefits (DOE, NAR, RESO, NASEO, etc.) are likely underutilized for marketing purposes. Marketing must identify and flag opportunities to owning divisions.

D. Objectives

What do you need to accomplish?

1. Establish Pearl as THE authority on home performance ratings in the real estate industry

2. Build investor credibility through visible market momentum ahead of Series B

3. Create measurable momentum within 90 days that can be documented for investors

4. Drive the 'claiming flywheel'—buyer awareness that drives seller claiming behavior

E. Success Criteria

How will you know if you accomplished it?

1. Tier-1 Media Placements: 6+ annually (WSJ, NYT, major RE publications)

2. Podcast Appearances: 4-6 per month systematic presence

3. Speaking Engagements: 6-8 annually at major RE/proptech conferences

4. Website Traffic: 25% quarter-over-quarter growth

5. Report Downloads: 500+ downloads per pillar content piece

6. Home Claims Trend: Measurable increase in claiming activity

F. Strategic Framework

The core approach and positioning.

1. 'Moments, Not Months' Approach

a) Concentrate spend around 4-6 major moments per year

b) $24K spread across 12 months = invisible

c) $24K concentrated in 2-3 moments = memorable

d) Splash comes from concentration, not distribution

2. Audience Priorities

a) Primary: Real estate agents, brokers, MLS executives

b) Secondary: Home buyers in transaction

3. Neutral Positioning (Critical)

a) Pearl IS: The standard for home performance data; transaction-facilitating; neutral

b) Pearl is NOT: A tool to help sellers get more money; a judge of 'good' vs. 'bad' homes

c) First Street lesson: Avoid being perceived as transaction-blocking

G. Budget Framework

Resource allocation model.

1. Fixed Costs: ~$7,500/month

a) Atkinson Strategic Group (PR): $4,500/month

b) Front Page Sage (SEO/Content): ~$3,000-5,000/month

2. Variable Allocation (% of remaining budget):

a) Paid Surge Fund (LinkedIn/Social): 28%

b) Geo-Fencing (Event Ads): 20%

c) Podcast Agency: 12%

d) Content Production: 12%

e) Contingency: 13%

f) Travel/Local TV: 6%

g) Retargeting: 5%

h) Tools: 4%

H. 2026 Moment Calendar

Major moments for concentrated investment.

Q1 Moments:

a) Inman Connect NYC (Feb 3-5) + 'State of Home Performance 2026' launch

b) IBS geo-fencing (Feb 17-19, builder audience)

Q2 Moments:

a) T3 Leadership Summit (Apr 22-24) + RESO Spring (Apr 21-23)

b) NAR Sustainability Summit (June)

Q3 Moments:

a) Inman Connect San Diego (Jul 28-30)

b) Partnership announcement (TBD)

Q4 Moments:

a) NAR NXT (Nov 6-8, New Orleans)

b) Year-end recap + 2027 preview

I. Channel Strategy

How we reach our audiences.

1. PR/Media (Atkinson): 20 pitches/month, press releases, podcast pitching

2. SEO/Content B2C (Front Page Sage): ~4 blog posts/month, weekly LinkedIn

3. Content B2B (Marketing + AI): Agent-focused content, pillar pieces, email sequences

4. Paid Media (Marketing): Surge model during moments, geo-fencing at conferences

5. Speaking (Cross-functional): Marketing supports with content; divisions own relationships and submissions

J. Resource Model

How we execute with a lean team.

1. Marketing Lead (1 person): Strategy, coordination, quality control, vendor management

2. AI Assistance (Claude): Content drafting, analysis, research, execution support

3. Outsourced Execution:

a) Atkinson: PR, media relations, podcast pitching

b) Front Page Sage: SEO content, LinkedIn

c) Potential: Podcast booking agency ($1,500-2,500/month)

4. Partnership Leverage:

a) Marketing FLAGS opportunities to owning divisions

b) Marketing SUPPORTS with content/collateral when divisions activate

c) Marketing does NOT own partnership relationships

K. Discussion Questions for Workshop

Key decisions needed from leadership.

1. Which moments should we prioritize if budget is constrained?

2. What is the realistic speaking engagement budget for paid slots?

3. Who owns conference attendance decisions (Marketing vs. BD)?

4. Which partnerships should marketing actively support vs. observe?

5. What does 'visible momentum' look like to the board specifically?

6. Should we invest in a podcast booking agency for additional reach?

7. How do we coordinate the Inman NYC moment with the existing Early Access campaign?

L. Attachments

Related documents.

1. 90-Day Sprint Plan (detailed execution)

2. Pearl_Budget_Calculator.xlsx

3. Pearl_Conference_Audit.xlsx

4. Pearl_Partnership_Audit.xlsx

5. Conference_Expansion_Analysis.md

pearlscore.com